## week1
Computer Science 2 Project | Team Members: | Laguiles, Alexis Tiffany T.
Group Progress Report |  | Salentes, Christine Hanne V.
3rd Quarter
Week 1 - Jan 16, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
research on how each of our features can be implemented into the program | dictionary on the different tasks | started on the code
start on the basic coding | datetime library | properly tracked date and time
STRENGTH
we were able to properly track date and time
AREAS FOR DEVELOPMENT
storing user information alongside schedule information
STRATEGY FOR SUCCESS
make progress everyday and test out every update/change to the program

## week2
Computer Science 2 Project | Team Members: | Laguilles, Alexis Tiffany T.
Group Progress Report |  | Salentes, Christine Hanne V.
3rd Quarter
Week 2 - Jan 23, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
start on the coding | Tkinter Library | Fixed bugs in preious codes
Learn about how to implement a GUI | Datetime Library | Working on the GUI
Fix bugs in previous codes | Dictionary on different tasks
STRENGTH
We were able to fix bugs, understand what is needed for the different components of our program and work efficiently as a duo
AREAS FOR DEVELOPMENT
Storing user information and the user's schedule info
STRATEGY FOR SUCCESS
keep debugging, testing, and make progress each day

## week3
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 3 - Jan 30, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS

## week4
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 4 - Feb 6, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS